## Sheet1
|  | MRT SSP LINE V201 PACKAGE | [180 empty] | MRT SSP LINE V201 PACKAGE
|  | OVERALL GUIDEWAY FACILITIES PROGRESS SCHEMATIC DIAGRAM | [180 empty] | OVERALL GUIDEWAY FACILITIES PROGRESS SCHEMATIC DIAGRAM
[155 empty] | SBN14 | [7 empty] | SBN15 | [8 empty] | SBN16
[103 empty] | SB08 |  |  |  | 30.792m |  |  |  |  | SB09 |  |  | 30.202m | [6 empty] | SB10 |  |  |  | 30.792m |  |  | SB11 |  |  |  | 30.788m |  |  |  |  | SB12 |  |  |  | 30.792m | [5 empty] | SB13 |  |  | 33.8n |  |  |  | SBS14 |  |  |  | 35.112m |  |  |  | SBS15 |  |  |  | 39.8m |  |  |  |  | SBS16 |  |  |  |  | 39.8m
|  | DD01 |  |  |  |  | 39.8m |  |  |  | SB01 |  |  | 33.125m |  |  | SB02 |  |  |  | 39.8m |  |  |  | SB03 | [7 empty] | 70m | [7 empty] | SB04 | [11 empty] | 110m | [10 empty] | SB05 | [9 empty] | 88m | [7 empty] | SB06 | [6 empty] | 44m | [5 empty] | SB07 |  |  |  |  | 39.8m
[196 empty] | SBS16 | [10 empty] | DDS01 | [7 empty] | 30m |  |  |  |  | DDS02 | [7 empty] | 26.225m | [6 empty] | DDS03 | [7 empty] | 33.775m | [6 empty] | DDS04 | [8 empty] | 30m |  |  |  |  | DDS05 | [6 empty] | 39.8m |  |  |  | DDS06
|  |  | DDN01 | [8 empty] | DDN02 | [5 empty] | DDN03 | [8 empty] | DDN04 | [7 empty] | DDN05 | [7 empty] | DDN06
|  |  | DDS01 |  |  |  | 30m |  |  |  |  | DDS02 |  |  | 26.225m |  |  | DDS03 |  |  |  |  | 33.775m |  |  |  | DDS04 |  |  | 30m |  |  |  |  | DDS05 |  |  |  | 39.8m |  |  |  | DDS06 |  |  | 29.693m |  |  |  | DD07 |  |  |  |  | 33.492m |  |  |  | DD08 |  |  | 33.383m |  |  |  | DD09 |  |  |  | 39.505m |  |  | DD10 |  | 35.255m |  |  |  |  | DD11 |  |  |  | 34.745m |  |  |  | DD12 |  |  |  |  | 39.8m |  |  |  | DD13 |  |  |  |  | 39.8m |  |  |  | DD14 |  |  |  |  | 39.8m |  |  | DD15 |  |  |  |  | 39.8m |  |  |  |  | DDN16 |  |  |  | 39.8m |  |  |  | DD17 |  |  |  | 39.8m |  |  |  | DD18 |  |  |  |  | 39.8m |  |  |  |  | DD19 |  |  | 39.8m |  |  |  |  | DD20 |  |  |  | 39.8m |  |  |  | DD21 |  |  |  |  | 33.6m |  |  |  | DD22 |  |  | 36.8m | [22 empty] | Piles: 0/4 | [18 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [13 empty] | Piles: 0/4
[214 empty] | Piles: 0/4 | [12 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [12 empty] | Piles: 0/4 | [12 empty] | Piles: 0/4
[198 empty] | SBN16 | [11 empty] | DDN01 | [5 empty] | Piles: 0/4 | [6 empty] | DDN02 | [5 empty] | Piles: 0/4 | [8 empty] | DDN03 | [6 empty] | Piles: 0/4 | [7 empty] | DDN04 | [6 empty] | Piles: 0/4 | [6 empty] | DDN05 | [10 empty] | DDN06
[182 empty] | 143 | [14 empty] | Piles: 0/4 | [11 empty] | Piles: 0/4 | [12 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [13 empty] | Piles: 0/4 | [10 empty] | Piles: 0/4
DDN28
| DD23 |  |  |  |  | 36.8m |  |  |  | DD24 |  |  | 33.8m |  |  |  | DD25 |  |  | 31.157m |  |  |  |  | DD26 |  |  | 36.8m | [5 empty] | DD27 |  |  | 39.8m |  |  |  |  | DDS28 |  |  | 29.831m |  |  | DD29 |  |  |  |  | 30.8m |  |  |  | DD30 |  |  |  | 39.8m |  |  |  | DD31 |  |  |  | 30.8m |  | DD32 |  |  | 34.109m |  |  |  | DD33 |  |  |  | 39.8m |  |  |  | DD34 |  |  |  |  | 30.8m |  |  |  | DD35 |  |  |  |  | 27.8m |  |  |  | DD36 |  |  |  |  | 39.8m |  |  | DD37 |  |  |  | 23m | [5 empty] | DD38 |  |  |  | 24.8m |  |  | DD39 | [7 empty] | 68m | [8 empty] | DD40 | [11 empty] | 100m | [9 empty] | DD41 | [6 empty] | 63m |  |  |  | DD42
[209 empty] | SDW01 | [6 empty] | 30m |  |  |  |  | SDW02 | [6 empty] | 26.225m | [7 empty] | SDW03 | [7 empty] | 33.775m | [6 empty] | SDW04 | [8 empty] | 30m |  |  |  |  | SDW05 | [5 empty] | 33.744m |  |  |  |  | SDW06
[17 empty] | DDN44 | [7 empty] | DDN45
| DD42 |  |  |  |  | 30.5m |  |  |  | DD43 |  |  | 30.8m |  |  |  | DDS44 |  |  |  | 30.8m |  |  |  | DDS45 |  |  | 30.8m | [5 empty] | DD46 |  |  | 30.736m |  |  |  |  | DD47 |  |  | 23.269m |  |  | DD48 |  |  |  |  | 27.8m |  |  |  | SDW01 |  |  | 30m |  |  |  | SDW2 |  |  | 26.225m |  |  |  | SDW03 |  |  | 33.775m |  |  |  | SDW04 |  |  | 30m |  |  |  |  | SDW05 |  |  |  | 33.744m |  |  |  |  | SDW06 |  |  |  | 33.571m |  |  |  | SDW07 |  |  |  | 35.655m |  |  |  |  | SDW08 |  |  | 39.429m | [5 empty] | SDW09 |  |  |  | 18.632m |  |  |  | SDW10 |  |  |  | 30.552m |  |  |  |  | SDW11 |  |  |  |  | 18.667m | [5 empty] | SDW12 |  |  | 39.8m |  |  |  | SDW13 |  |  |  | 34.119m |  |  |  | SDW14 |  |  |  |  | 36.8m |  |  | SDW15 |  |  |  | 39.8m |  |  |  | SDW15
[193 empty] | Piles: 0/4 | [8 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [13 empty] | Piles: 0/4 | [15 empty] | Piles: 0/4 | [13 empty] | Piles: 0/4 | [10 empty] | Piles: 0/4
[211 empty] | Piles: 0/4 | [12 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4
[23 empty] | DDN44 | [6 empty] | DDN45
| SDW16 |  |  |  | 39.8m |  |  |  |  | SDW17 |  |  |  | 39.8m |  |  | SDW18 |  |  |  | 39.8m |  |  |  | SDW19 |  |  |  | 39.8m |  |  |  |  | SDW20 |  |  | 39.8m |  |  |  |  | SDW21 |  |  | 39.8m |  |  | SDW22 |  |  |  |  | 33.8m |  |  |  | SDW23 |  |  | 36.8m |  |  |  |  | SDW24 |  |  | 39.8m |  |  | SDW25 |  |  | 39.8m |  |  |  | SDW26 |  |  |  | 39.8m |  |  | SDW27 |  |  |  | 39.8m | [5 empty] | SDW28 |  |  |  | 39.8m |  |  |  |  | SDW29 |  |  |  | 39.8m |  |  |  | SDW30 |  |  | 39.8m | [5 empty] | SDW31 |  |  |  | 30.8m |  |  |  | SDW32 |  |  |  | 29.667m |  |  |  |  | SDW33 |  |  |  | 39.8m |  |  |  |  | SDW34 |  |  |  | 39.8m |  |  |  | SDW35 | [6 empty] | 52m | [6 empty] | SDW36 |  |  |  | 78m | [7 empty] | SDW37
[190 empty] | SDW41 |  |  |  | 30.8m |  |  |  |  | SDE01 |  |  |  |  | 30m | [7 empty] | SDE02 | [6 empty] | 30m | [5 empty] | SDE03 | [7 empty] | 30m | [6 empty] | SDE04 | [7 empty] | 33.8m | [6 empty] | SDE05 | [6 empty] | 23.067m | [5 empty] | SDE06 | [5 empty] | 39.8m | [5 empty] | SDE07
[191 empty] | Piles: 0/4 | [8 empty] | Piles: 0/4 | [12 empty] | Piles: 0/4 | [12 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [14 empty] | Piles: 0/4 | [12 empty] | Piles: 0/4
| SDW37 | [6 empty] | 52m | [6 empty] | SDW38 |  |  | 39.8m |  |  |  | SDW39 |  |  |  | 34.092m |  |  |  | SDW40 |  |  |  |  | 39.8m |  |  | SDW41 |  |  |  |  | 30.8m |  |  | SDE01 |  |  | 30m |  |  |  |  | SDE02 |  |  |  | 30m |  |  |  | SDE03 |  |  |  | 30m |  |  |  | SDE04 |  | 33.8m |  |  | SDE05 |  |  |  | 23.067m |  |  |  | SDE06 |  |  |  | 39.8m |  |  |  |  | SDE07 |  |  |  | 39.8m |  |  |  |  | SDE08 |  |  |  | 39.8m |  |  |  |  | SDE09 |  |  | 39.8m |  |  |  | SDE10 | [5 empty] | 31.782m |  |  |  | SDE11 |  |  |  | 39.8m |  |  | SDE12 |  |  |  |  | 39.8m |  |  |  |  | SDE13 |  |  |  |  | 31.575m |  |  | SDE14 |  |  |  |  | 33.8m |  |  |  | SDE15 |  |  |  | 33.8m |  |  |  |  | SDE16 |  |  |  | 36.8m
SDE17 |  |  |  | 36.8m |  |  |  |  | SDE18 |  |  |  | 33.5m |  |  | SDE19 |  |  | 33.8m |  |  |  |  | SDE20 |  |  |  | 39.8m |  |  |  | SDE21 |  |  |  | 39.8m |  |  |  | SDE22 |  |  |  | 33.8m |  |  | SDE23 |  |  |  | 39.8m |  |  |  |  | SDE24 |  |  |  | 30.8m |  |  |  | SDE25 |  |  |  | 30.8m
PROGRESS TO DATE :
PROGRESS TO DATE :
[89 empty] | TOTAL SPAN (SBG) | [16 empty] | : |  | 0 | [11 empty] | SPAN LAUNCHED TO DATE (SBG) | [20 empty] | : |  | 0 | [10 empty] | PERCENT COMPLETE | [16 empty] | : | #DIV/0!
|  | TOTAL GUIDEWAY BORED PILES | [15 empty] | : | 493 | [11 empty] | GUIDEWAY PILES COMPLETED TO DATE | [18 empty] | : |  | 0 | [10 empty] | PERCENT COMPLETE | [12 empty] | : | 0% | [163 empty] | TOTAL SPAN (SBG) | [14 empty] | : |  | 0 | [9 empty] | SPAN LAUNCHED TO DATE (SBG) | [15 empty] | : | 0 | PERCENT COMPLETE | : | #DIV/0!
[184 empty] | TOTAL GUIDEWAY BORED PILES |  | : | 485 |  |  |  | GUIDEWAY PILES COMPLETED TO DATE | [11 empty] | : |  | 0 | [9 empty] | PERCENT COMPLETE | [12 empty] | : |  | 0%
|  | TOTAL GUIDEWAY SPUN PILES | [15 empty] | : | 0 | [11 empty] | GUIDEWAY PILES COMPLETED TO DATE | [18 empty] | : |  | 0 | [10 empty] | PERCENT COMPLETE | [12 empty] | : | #DIV/0! | [163 empty] | TOTAL U-BEAMS | [14 empty] | : |  | 0 | [9 empty] | U-BEAM CASTED TO DATE | [15 empty] | : | 0 | PERCENT COMPLETE | : | #DIV/0!
[184 empty] | TOTAL GUIDEWAY SPUN PILES |  | : | 0 |  |  |  | GUIDEWAY PILES COMPLETED TO DATE | [11 empty] | : |  | 0 | [9 empty] | PERCENT COMPLETE | [12 empty] | : |  | #DIV/0!
0
|  | TOTAL GUIDEWAY PILECAPS | [15 empty] | : | 143 | [11 empty] | GUIDEWAY PILECAPS COMPLETED TO DATE | [18 empty] | : |  | 0 | [10 empty] | PERCENT COMPLETE | [12 empty] | : | 0% | [127 empty] | 0 | [62 empty] | U-BEAM LAUNCHED TO DATE | [15 empty] | : | 0 | PERCENT COMPLETE | : | #DIV/0!
[184 empty] | TOTAL GUIDEWAY PILECAPS |  | : | 143 |  |  |  | GUIDEWAY PILECAPS COMPLETED TO DATE | [11 empty] | : |  | 0 | [9 empty] | PERCENT COMPLETE | [12 empty] | : |  | 0%
0
|  | TOTAL GUIDEWAY PIER COLUMNS | [15 empty] | : | 143 | [11 empty] | GUIDEWAY PIER COLUMNS COMPLETED TO DATE | [18 empty] | : |  | 0 | [10 empty] | PERCENT COMPLETE | [12 empty] | : | 0% | [14 empty] | LEGENDS : | [112 empty] | 0 | [35 empty] | TOTAL SPAN (U-BEAM) | [14 empty] | : |  | 0 | [9 empty] | SPAN LAUNCHED TO DATE (U-BEAM) | [15 empty] | : | 0 | PERCENT COMPLETE | : | #DIV/0!
[184 empty] | TOTAL GUIDEWAY PIER COLUMNS |  | : | 143 |  |  |  | GUIDEWAY PIER COLUMNS COMPLETED TO DATE | [11 empty] | : |  | 0 | [9 empty] | PERCENT COMPLETE | [12 empty] | : |  | 0%
0
|  | TOTAL GUIDEWAY PIER HEADS | [15 empty] | : | 155 | [11 empty] | GUIDEWAY PIER HEADS COMPLETED TO DATE | [18 empty] | : |  | 0 | [10 empty] | PERCENT COMPLETE | [12 empty] | : | 0% | [127 empty] | 0 | [35 empty] | LEGENDS :
[98 empty] | SBG | [12 empty] | PILING / PILECAP / PIER/ PIERHEAD - IN PROGRESS | [23 empty] | SEGMENTAL BOX GIRDER CASTED | [48 empty] | TOTAL GUIDEWAY PIER HEADS |  | : | 140 |  |  |  | GUIDEWAY PIER HEADS COMPLETED TO DATE | [11 empty] | : |  | 0 | [9 empty] | PERCENT COMPLETE | [12 empty] | : |  | 0%
0
|  | DD STATION PILES | [15 empty] | : | 32 | [11 empty] | STATION PILES COMPLETED TO DATE | [18 empty] | : |  | 0 | [10 empty] | PERCENT COMPLETE | [12 empty] | : | 0% | [127 empty] | 0
[98 empty] | Span | [12 empty] | PILING / PILECAP / PIER / PIERHEAD- COMPLETED | [23 empty] | SEGMENTAL BOX GIRDER LAUNCHED | [48 empty] | DD STATION PILES |  | : | 40 |  |  |  | STATION PILES COMPLETED TO DATE | [11 empty] | : |  | 0 | [9 empty] | PERCENT COMPLETE | [12 empty] | : |  | 0% | [18 empty] | SBG | [8 empty] | PILING / PILECAP / PIER/ PIERHEAD - IN PROGRESS | [17 empty] | SEGMENTAL BOX GIRDER / U-BEAM CASTED
0
|  | SDW STATION PILES | [15 empty] | : | 16 | [11 empty] | SEGMENTAL BOX GIRDER CASTED TO DATE | [18 empty] | : |  | 0 | [10 empty] | PERCENT COMPLETE | [12 empty] | : | 0% | [127 empty] | 0
[184 empty] | SDW STATION PILES |  | : | 20 |  |  |  | SEGMENTAL BOX GIRDER CASTED TO DATE | [11 empty] | : |  | 0 | [9 empty] | PERCENT COMPLETE | [12 empty] | : |  | 0% | [18 empty] | U-BEAM | [8 empty] | PILING / PILECAP / PIER / PIERHEAD- COMPLETED | [17 empty] | SEGMENTAL BOX GIRDER / U-BEAM LAUNCHED
[94 empty] | PIERHEAD | [14 empty] | PIERHEAD | [8 empty] | PIERHEAD | [11 empty] | PIERHEAD
|  | SDE STATION PILES | [15 empty] | : | 0 | [11 empty] | SEGMENTAL BOX GIRDER LAUNCHED TO DATE | [18 empty] | : |  | 0 | [10 empty] | PERCENT COMPLETE | [12 empty] | : | 0%
[95 empty] | PIER | [14 empty] | PIER | [8 empty] | PIER | [11 empty] | PIER | [53 empty] | SDE STATION PILES |  |  | : | 16 |  |  | SEGMENTAL BOX GIRDER LAUNCHED TO DATE | [13 empty] | : |  | 0 | [9 empty] | PERCENT COMPLETE | [13 empty] | : |  | 0% | [13 empty] | PIERHEAD | [9 empty] | PIERHEAD | [7 empty] | PIERHEAD | [6 empty] | PIERHEAD | [7 empty] | PIERHEAD
|  | TOTAL STATION PILES | [15 empty] | : | 48 | [75 empty] | PILECAP | [14 empty] | PILECAP | [8 empty] | PILECAP | [11 empty] | PILECAP | [117 empty] | PIER | [9 empty] | PIER | [7 empty] | PIER | [6 empty] | PIER | [7 empty] | PIER
[185 empty] | TOTAL STATION PILES |  |  | : | 76
[95 empty] | PILES | [14 empty] | PILES | [8 empty] | PILES | [11 empty] | PILES | [117 empty] | PILECAP | [9 empty] | PILECAP | [7 empty] | PILECAP | [6 empty] | PILECAP | [7 empty] | PILECAP
|  | TOTAL SEGMENTAL BOX GIRDER | [15 empty] | : | 1768
[93 empty] | STANDARD PIER | [9 empty] | PORTAL PIER | [10 empty] | CANTILEVER PIER | [12 empty] | CROSSHEAD PIER | [57 empty] | TOTAL SEGMENTAL BOX GIRDER |  |  | : | 357 | [59 empty] | PILES | [9 empty] | PILES | [7 empty] | PILES | [6 empty] | PILES | [7 empty] | PILES
`
[195 empty] | ` | [50 empty] | STANDARD PIER | [6 empty] | PORTAL PIER | [9 empty] | CANTILEVER PIER | [7 empty] | CROSSHEAD PIER | [7 empty] | STATION PIER
DAMANSARA DAMAI STATION (ISLAND PLATFORM)
SPECIAL CROSSING (70 + 110 + 88 + 44)
SRI DAMANSARA WEST STATION (ISLAND PLATFORM)
SPECIAL CROSSING (52 - 78 - 52)
SRI DAMANSARA EAST STATION (SIDE PLATFORM)
SPECIAL CROSSING (68 - 100 - 63)
12 nos. Single Pile Near Syabas Water Tanks (RCD method)
SRI DAMANSARA WEST STATION (ISLAND PLATFORM)
Piles: 0/20, Pilecaps: 0/20
DAMANSARA DAMAI STATION (ISLAND PLATFORM)
Piles: 0/40, Pilecaps: 0/40
SRI DAMANSARA EAST STATION (SIDE PLATFORM)
Piles: 0/16, Pilecaps: 0/16
MERGING SPAN
MERGING SPAN
MERGING SPAN
(0/4)
(0/4)
(0/4)
(0/8)
(0/8)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/6)
(0/8)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/2)
(0/2)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/6)
(0/6)
(0/6)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/6)
(0/6)
(0/2)
(0/2)
(0/6)
(0/6)
(0/1)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/6)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/1)
(0/1)
(0/1)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/1)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)
(0/4)