## Piling Chart
MRT SSP LINE PACKAGE V202: CONSTRUCTION AND COMPLETION OF VIADUCT GUIDEWAY AND OTHER ASSOCIATED WORKS FROM PERSIARAN DAGANG TO JINJANG
OVERALL GUIDEWAY FACILITIES PROGRESS SCHEMATIC DIAGRAM
T-shape TSR Type 1A
T-shape TSR Type 2A & 2B
T-shape TSP Type 3A & 3B
T-shape TSP Type 4A,4A1,4B & 4B1
MRT SSP LINE PACKAGE V202: CONSTRUCTION AND COMPLETION OF VIADUCT GUIDEWAY AND OTHER ASSOCIATED WORKS FROM PERSIARAN DAGANG TO JINJANG
OVERALL GUIDEWAY FACILITIES PROGRESS SCHEMATIC DIAGRAM
PROGRESS TO DATE:
Total Guideway Bored Piles |  | : | 649 | Guideway Piles Completed To Date | : | 0 | Percent Completed | : | 0
Total Guideway Pilecaps |  | : | 161 | Guideway Pilecaps Completed To Date | : | 0 | Percent Completed | : | 0
Total Guideway Pier |  | : | 161 | Guideway Pier Columns Completed To Date | : | 0 | Percent Completed | : | 0
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE27
(0/4)
SDE28
(0/4)
SDE29
(0/4)
SDE30
(0/4)
SDE31
(0/4)
SDE32
(0/4)
SDE33
(0/4)
SDE34
(0/4)
SDE35
(0/4)
SDEN36
(0/4)
SDES36
(0/4)
SDE37
(0/4)
SDEN38
(0/4)
SDES38
(0/4)
KS01
(0/4)
KS2/A
(0/4)
KS02
(0/4)
KS4/D
(0/4)
KS03
(0/4)
KS6/D
(0/4)
KS04
(0/4)
KS8/D
(0/4)
KS05
(0/4)
KS06
(0/4)
KS07
(0/4)
KS08
(0/4)
KS09
(0/4)
KS10
(0/4)
KS11
(0/4)
KS12
(0/4)
KS13
(0/4)
KS14
(0/4)
KS15
(0/4)
KS16
(0/4)
KS17
(0/4)
KS18
(0/4)
KS19
(0/4)
KS20
(0/4)
KS21
(0/4)
KS22
(0/4)
KS23
(0/4)
KS24
(0/4)
KS25
(0/4)
KS26
(0/4)
KS27
(0/4)
KS28
(0/5)
KS29
(0/4)
KS35
(0/4)
KS36
(0/4)
KS37
(0/4)
KS30
(0/4)
KS31
(0/4)
KS32
(0/4)
KS33
(0/4)
KS34
(0/4)
KS38
(0/4)
KSN39
(0/4)
KSN40
(0/4)
KSS39
(0/4)
KSS40
(0/4)
KSN41
(0/4)
KSS41
(0/4)
KS42
(0/4)
KS43
(0/4)
KS44
(0/4)
KS45
(0/4)
MP01
(0/4)
MP02
(0/4)
MP03
(0/4)
MP04
(0/4)
MP05
(0/4)
MP06
(0/4)
MP07
(0/4)
MP08
(0/4)
MP09
(0/4)
MP10
(0/4)
MP11
(0/6)
MP12
(0/4)
MP13
(0/4)
MP14
(0/4)
MP15
(0/4)
MP16
(0/4)
MP17
(0/4)
MP18
(0/4)
MP19
(0/6)
MP20
(0/4)
MP21
(0/4)
MP22
(0/4)
MP23
(0/4)
MP24
(0/4)
MP25
(0/4)
MP26
(0/4)
MP27
(0/4)
MP28
(0/4)
MP29
(0/4)
J1/E
(0/4)
J1/A
(0/4)
KBN01
(0/4)
KBS01
(0/4)
JN05
(0/4)
KBN02
(0/4)
KBS02
(0/4)
KBN03
(0/4)
KBS03
(0/4)
KBN04
(0/4)
KBS04
(0/4)
KBN05
(0/4)
KBS05
(0/4)
KBN06
(0/4)
KBS06
(0/4)
KBN07
(0/4)
KBS07
(0/4)
KBN08
(0/4)
KBS08
(0/4)
KBN09
(0/4)
KBS09
(0/4)
KB10
(0/4)
KB11
(0/4)
KB12
(0/4)
KB13
(0/4)
KB14
(0/4)
KB15
(0/4)
KB16
(0/4)
KB17
(0/4)
KB18
(0/4)
KB19
(0/4)
KB20
(0/4)
KBN21
(0/4)
KBS21
(0/4)
KBN22
(0/4)
KBS22
(0/4)
KBN22
(0/4)
KBS22
(0/4)
KBN23
(0/4)
KBS23
(0/4)
KBN24
(0/4)
KBS24
(0/4)
JN01
(0/4)
JS01
(0/4)
JN02
(0/4)
JS02
(0/4)
J3/E
(0/4)
J3/A
(0/4)
JN03
(0/4)
JS03
(0/4)
J5/E
(0/4)
J5/A
(0/4)
JN04
(0/4)
JS04
(0/4)
J7/E
(0/4)
J7/A
(0/4)
JS05
(0/4)
J06
(0/4)
J07
(0/4)
J08
(0/4)
J09
(0/4)
J10
(0/4)
J11
(0/4)
J12
(0/4)
KS2/G
(0/4)
KEPONG SENTRAL STATION
METRO PRIMA STATION
KEPONG BARU STATION
JINJANG STATION
LONG SPAN NO. 4 (crossing underneath MRR2)
(0/15)
(0/15)
(0/15)
(0/4)
(0/4)
LONG SPAN NO. 5 (crossing Sungai Keroh)
(0/15)
(0/29)
(0/5)
(0/7)
Pocket Track
Pocket Track

## Piling Chart (2)
MRT SSP LINE PACKAGE V202: CONSTRUCTION AND COMPLETION OF VIADUCT GUIDEWAY AND OTHER ASSOCIATED WORKS FROM PERSIARAN DAGANG TO JINJANG
OVERALL GUIDEWAY FACILITIES PROGRESS SCHEMATIC DIAGRAM
T-shape TSR Type 1A
T-shape TSR Type 2A & 2B
T-shape TSP Type 3A & 3B
T-shape TSP Type 4A,4A1,4B & 4B1
MRT SSP LINE PACKAGE V202: CONSTRUCTION AND COMPLETION OF VIADUCT GUIDEWAY AND OTHER ASSOCIATED WORKS FROM PERSIARAN DAGANG TO JINJANG
OVERALL GUIDEWAY FACILITIES PROGRESS SCHEMATIC DIAGRAM
|  | : | 120 | Guideway Piles Completed To Date |  | : | 0 |  | Percent Completed | : | 0
|  | : | 19 | Guideway Pilecaps Completed To Date |  | : | 0 |  | Percent Completed | : | 0
PROGRESS TO DATE:
|  | : | 19 | Guideway Pier Columns Completed To Date |  | : | 0 |  | Percent Completed | : | 0
Total Guideway Bored Piles |  | : | 19 | Guideway Pier Heads Completed To Date |  | : | 0 |  | Percent Completed | : | 0
Total Guideway Pilecaps
Total Guideway Pier Columns
|  |  |  | : | Total Micropile for Temporary Decking |  |  | :
Total Guideway Pier Heads
:
TEMPORARY WORK PROGRESS TO DATE:
Total Permanent Sheetpile for River Realignment (200m)
Total Sheetpile Retaining Wall (Highway Interchage)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE26
(0/4)
SDE27
(0/4)
SDE28
(0/4)
SDE29
(0/4)
SDE30
(0/4)
SDE31
(0/4)
SDE32
(0/4)
SDE33
(0/4)
SDE34
(0/4)
SDE35
(0/4)
SDE36N
(0/4)
SDE36S
(0/4)
SDE37
(0/4)
SDE38N
(0/4)
SDE38S
(0/4)
KS01N
(0/4)
KS01S
(0/4)
KS02N
(0/4)
KS02S
(0/4)
KS02N
(0/4)
KS02S
(0/4)
KS04N
(0/4)
KS04S
(0/4)
KS03N
(0/4)
KS03S
(0/4)
SDE26
(0/4)
SDE26
(0/4)
KS04N
(0/4)
KS04S
(0/4)
SDE26
(0/4)
SDE26
(0/4)
KS05N
(0/4)
KS05S
(0/4)
KS06
(0/4)
KS07
(0/4)
KS08
(0/4)
KS09
(0/4)
KS10
(0/4)
KS11
(0/4)
KS12
(0/4)
KS13
(0/4)
KS14
(0/4)
KS15
(0/4)
KS16
(0/4)
KS17
(0/4)
KS18
(0/4)
KS19
(0/4)
KS20
(0/4)
KS21
(0/4)
KS22
(0/4)
KS23
(0/4)
KS24
(0/4)
KS25
(0/4)
KS26
(0/4)
KS27
(0/4)
KS28
(0/4)
KS29
(0/4)
KS35
(0/4)
KS36
(0/4)
KS37
(0/4)
KS30
(0/4)
KS31
(0/4)
KS32
(0/4)
KS33
(0/4)
KS34
(0/4)
KS38
(0/4)
KS39N
(0/4)
KS40N
(0/4)
KS39S
(0/4)
KS40S
(0/4)
KS41N
(0/4)
KS41S
(0/4)
KS42
(0/4)
KS43
(0/4)
KS44
(0/4)
KS45
(0/4)
MP01
(0/4)
MP02
(0/4)
MP03
(0/4)
MP04
(0/4)
MP05
(0/4)
MP06
(0/4)
MP07
(0/4)
MP08
(0/4)
MP09
(0/4)
MP10
(0/4)
MP11
(0/4)
MP12
(0/4)
MP13
(0/4)
MP14
(0/4)
MP15
(0/4)
MP16
(0/4)
MP17
(0/4)
MP18
(0/4)
MP19
(0/4)
MP20
(0/4)
MP21
(0/4)
MP22
(0/4)
MP23
(0/4)
MP24
(0/4)
MP25
(0/4)
MP26
(0/4)
MP27
(0/4)
MP28
(0/4)
MP29
(0/4)
JN02
(0/4)
JS02
(0/4)
KBN01
(0/4)
KBS01
(0/4)
JN05
(0/4)
KBN02
(0/4)
KBS02
(0/4)
KBN03
(0/4)
KBS03
(0/4)
KBN04
(0/4)
KBS04
(0/4)
KBN05
(0/4)
KBS05
(0/4)
KBN06
(0/4)
KBS06
(0/4)
KBN07
(0/4)
KBS07
(0/4)
KBN08
(0/4)
KBS08
(0/4)
KBN09
(0/4)
KBS09
(0/4)
KB10
(0/4)
KB11
(0/4)
KB12
(0/4)
KB13
(0/4)
KB14
(0/4)
KB15
(0/4)
KB16
(0/4)
KB17
(0/4)
KB18
(0/4)
KB19
(0/4)
KB20
(0/4)
KBN21
(0/4)
KBS21
(0/4)
KBN22
(0/4)
KBS22
(0/4)
KBN22
(0/4)
KBS22
(0/4)
KBN23
(0/4)
KBS23
(0/4)
KBN24
(0/4)
KBS24
(0/4)
JN01
(0/4)
JS01
(0/4)
JN02
(0/4)
JS02
(0/4)
JN02
(0/4)
JS02
(0/4)
JN03
(0/4)
JS03
(0/4)
JN02
(0/4)
JS02
(0/4)
JN04
(0/4)
JS04
(0/4)
JN02
(0/4)
JS02
(0/4)
JS05
(0/4)
J06
(0/4)
J07
(0/4)
J08
(0/4)
J09
(0/4)
J10
(0/4)
J11
(0/4)
J11
(0/4)